## july
Date | Work details | Pending | Pending for Reason | Duration
2020-08-01 | DueDate Master creation (individual Menu) |  |  | 6 hours
2020-08-03 | Dashboard page Correction(related to admin view) |  |  | 7 hours
Statistics correction for dashboard page
Send updated correction page via mail
2020-08-04 | Adding paging and search option in DueDateMaster Menu |  |  | 7 hours
| show password function | alignment pending
Updated page uploaded to server
download the old page backup before uploading new page
| Discussion for internal Due date master( discussion not completed) | Pending | clear discussion not completed today
2020-08-05 | Show Password function Completed for all page |  |  | 7 hours
Statistics changes(user count page)
controller page changes (allow statistics view all user)
upload updated statistics page to server
download the old page backup before uploading new statistics page
backup page mail sent
2020-08-06 | add searchbox for every dropdown option | pending | every page have dropdown menu. | 6 hours 40 minutes
few pages are completed for add
search box dropdown
2020-08-07 | Searchbox adding every dropdown option in all page completed |  |  | 7 hours
2020-08-08 | send mail updated page (search box ) |  |  | 6 hours 40 minutes
| change Data management page data display based on user assign activity and admin based view |  | Pending Practise area based view
send mail server uploaded page details
2020-08-09 | send mail DataManagement design format
Discussion about dataManagement design and duedate master
2020-09-10 | DataManagement new design edit process | pending | Download relevant template master code | 7 hours
2020-09-11 | DataManagement page Relavant process and template master complete |  |  | 6 hours
2020-08-12 | DueDate Master page Days select box change to text box,edit and update page also complete |  |  | 6 hours
2020-08-13 | DueDate Master page upload to server |  |  | 7 hours
EditTask page error correction(Siva kumar sir told that error for updation) completed and upload to server
2020-08-14 | DueDate Master page month select box change to textbox with condition 1 to 12 |  |  | 6 hours
Updated DuedateMaster uploaded to server
2020-08-15 | Internal DueDate Master selectbox to textbox changes(remove hours column & add Notes Column) |  |  | 6 hours
Internal DueDate Master updated uploaded to server
taken old page backup from server
2020-08-16 | Old pages were discussed over the phone about the change,The Pages are Client Management,Task and ShortTask(Receiver Type change) |  |  | 5 hours(Sunday)
Upload updated DataManagement page into server
2020-08-17 | Documentation for Client Management changes
Documentation for Task and Short Management changes
| DataManagement Page Checking |  |  | 6 hours 20 minutes
Discussion over Documentation related checking again(via phone call)
Download sql table via mail
2020-08-18 | Dashboard User count list for All type of users
2020-08-19 | ShortTask Receiver type design created | (only Design created,function pending) |  | 6 hours 40 minutes
DataManagement issue Checking
2020-08-20 | DataManagement issue completed |  |  | 6 hours
change the Remainder to Reminder
| Client Management correction | pending
2020-08-21 | taken leave for Eye swelling pain
2020-08-22
2020-08-23 | Client Management changes ( secondary details insert and update) completed |  |  | 6 hours
2020-08-24 | DataManagement page uploaded to server
Dashboard user count of all users uploaded
2020-08-25 | short task changes completed. |  |  | 6 hours
short task updated page uploaded to server
backup pages are mailed